## Scorecard
INTEGRATED TRANSFORMATION KPI SCORECARD
Section | Metric | Baseline (M0) | Target (M18) | Actual (M18) | Variance % vs Target | Unit | Notes
SYNERGIES | Cost Synergies Realized | 0 | 47 | 40 |  | MUSD | Higher is better
SYNERGIES | Revenue Synergies | 0 | 23 | 19 |  | MUSD | Higher is better
SYNERGIES | Overall Synergy Achievement |  |  |  |  | % | Overall synergy = (Cost+Revenue Actual) / (Cost+Revenue Target)
DIGITAL | Digital Adoption (DAU) | 12 | 65 | 73 |  | % | Higher is better
TALENT | Fintech Talent Retention | 27 | 75 | 91 |  | % | Higher is better
TALENT | Overall Attrition Rate | 18 | 12 | 9 |  | % | Lower is better
TALENT | Engagement Score (10-pt) | 3.2 | 6 | 7.8 |  | score | Higher is better
OPERATIONAL | Decision Cycle Time (days) | 47 | 20 | 14 |  | days | Lower is better
OPERATIONAL | Process Efficiency Gain | 0 | 15 | 23 |  | % | Higher is better
OPERATIONAL | Customer Satisfaction (CSAT) | 72 | 75 | 81 |  | score | Higher is better
TIMELINE | Months to Completion | 24 | 24 | 18 |  | months | Lower is better
TIMELINE | Milestones Hit On-Time | 30 | 80 | 87 |  | % | Higher is better
FINANCIAL | ROI |  |  |  |  | x | ROI = (Cost+Revenue Actual) / Total Program Cost (25.7 MUSD)
*Overall synergy achievement = Total realized ($59M) / Total target ($70M) = 84.3%, rounded to 85%